## Login&Signup
Project Name | Furniture Market Place
module name | Login&Signup Page
created by | Mahmoud M.Abo Shark (Team Leader)
creation date | 2\5\2025
reviwed by | Moaaz Besher
reviwed date | 2025-05-09
executid by | Mahmoud M.Abo Shark
executid date | 2025-05-13
TC_ID | Title | Pre-condition | Steps | Test Data | Expected Result | Attachments if any | postcondition | Type | Status | Actual Result | BUG_ID | Created by | Reviewed by | Comments | executed by
TC_P_0001 | Facebook Login | User on homepage | 1. Click Login 2. Click Facebook button | N/A | Redirect to Facebook auth | N/A | On Facebook login page | Functional | Failed | Registration error inactive application | B_C_001 | Mahmoud Aboshark | Moaaz Besher | Facebook integration not working
TC_P_0002 | Google Login | User on homepage | 1. Click Login 2. Click Google button | N/A | Redirect to Google auth page | N/A | On Google auth page | Functional | Pass | Redirected to Google auth | _ | Mahmoud Aboshark | Moaaz Besher | _
TC_P_0003 | Valid Email Login | User on login page | 1. Enter email 2. Enter password 3. Click Login | Email: depitester1@gmail.com Pass: @Depi_Team#5 | "Login completed successfully" | N/A | User logged in | Functional | Pass | "Login completed successfully" displayed | _ | Mahmoud Aboshark | Moaaz Besher | _
TC_P_0004 | Invalid Email Login | User on login page | 1. Enter email 2. Enter wrong password 3. Click Login | Email: depitester1@gmail.com Pass: Testing20 | "Sorry, you couldn't log in..." | N/A | Error message shown | Functional | Pass | Correct error message displayed | _ | Mahmoud Aboshark | Moaaz Besher | _
TC_P_0005 | Forgot Password | User on login page | 1. Click Forgot Password 2. Enter email 3. Submit | Email: depitester1@gmail.com | "We've sent you a reset email..." | N/A | Password reset email sent | Functional | Pass | Correct success message displayed | _ | Mahmoud Aboshark | Moaaz Besher | _
TC_P_0006 | New User Signup | User on homepage | 1. Click Signup 2. Fill form 3. Accept terms | Email: Shark1@gmail.com new email you must change that Pass: @Depi_Team#5 | "Sign Up completed successfully" | N/A | New account created | Functional | Pass | Account created successfully | _ | Mahmoud Aboshark | Moaaz Besher | _
TC_P_0007 | Login Button UI | User on homepage | 1. Verify button exists 2. Verify click functionality | Email: depitester1@gmail.com Pass: @Depi_Team#5 | Button visible and functional | N/A | Login page accessible | UI | Pass | Button works correctly | _ | Mahmoud Aboshark | Moaaz Besher | _
TC_P_0008 | Signup Button UI | User on homepage | 1. Verify button exists 2. Verify click functionality | Email: Shark1@gmail.com new email you must change that Pass: @Depi_Team#5 | Button visible and functional | N/A | Signup page accessible | UI | Pass | Button works correctly | _ | Mahmoud Aboshark | Moaaz Besher | _
Bug Report
Defect-id | title | Description | Pre-condition | steps | postcondition | ER | AR | Severity | Priority | type | status | Version | Attachment
B_C_001 | Facebook Login Fail | Facebook Login FailRedirects to 401 error page | User clicks Facebook login | Click Facebook login button | Shows error page | Facebook auth page | 401 error page | High | High | Functional | Open | demo

## Homepage & Search
Project Name | Furniture Market Place
module name | Homepage & Search
created by | Mahmoud A.Elsherbiny
link project | https://demo.getmarketspace.com
reviwed by | Amina
reviwed date | 11\5\2025
creation date | 2\5\2025
executid date | 4\5\2025
TC_ID | Title | Pre-condition | Steps | Test Data | Expected Result | Attachments if any | postcondition | Type | Status | Actual Result | BUG_ID | Created by | Reviewed by | Comments | executed by
TC_P_0001 | verify search with vaild product name | User is on Homepage | 1- Enter " Chair " in search bar 2- Click search button | chair | Products related to " chair " are displayed. | N/A | Relevant searsh results displayed | Functional | PASS | Successfully displayed patient diagnosis |  | Mahmoud Elsherbiny | Amina | Positive
TC_P_0002 | Verify search with Location | User is on Homepage | 1- Enter " Cairo " in Search bar 2- Click search button | Location "Cairo" | Show in Product for " Cairo " | N/A | Relevant searsh results displayed | Functional | Failed | Failed to store search results | not seach Product | Mahmoud Elsherbiny | Amina | Negative
TC_P_0003 | Verify category with products | User is on Homepage | 1. Click on a category with products (e.g., test category). | Test Cataegory | 1-Show page Categories and click any category 2- Show in page Products and choose any products | N/A | Search results cleared | Functional | PASS | Categories and goals displayed correctly |  | Mahmoud Elsherbiny | Amina | Positive
TC_P_0004 | check click image products | User is on Homepage | click left on imege | image | Show in Pruchese page | N/A | Search results cleared | UI | PASS | Chinese page loaded successfully |  | Mahmoud Elsherbiny | Amina | Positive
TC_P_0005 | click the Cart | User is on Homepage | Click left on the cart | Cart | 1-Show in shopping cart 2- Show Selected products | N/A | Product successfully added to cart | UI | PASS | Cart details and offers displayed correctly |  | Mahmoud Elsherbiny | Amina | Positive
TC_P_0006 | Verify the logo page | User is on Homepage | click on the logo page | Iogo | Home Page display | N/A | Search results cleared | UI | PASS | Homepage loaded successfully |  | Mahmoud Elsherbiny | Amina | Positive
TC_P_0007 | Verife homepage navigation | User is on another page | Click the homepage link from the navigation bar | Homepage link | Homepage loads correctly | N/A | User is on homepage | Navigation | PASS | Successfully navigated to homepage |  | Mahmoud Elsherbiny | Amina | Positive
TC_P_0008 | verife bannar image functionallity | User is on Homepage | Click on the bannar image | Bannar image | Redirects to the promotional page | N/A | User is redirected to correct page | Functional | PASS | Successfully redirected to profile page |  | Mahmoud Elsherbiny | Amina | Positive
TC_P_0009 | check featured products section | User is on Homepage | Scroll down to "Featured Products" | None | All featured products are displayed correctly | N/A | Featured product are loaded and visible | Validation | PASS | All features verified successfully |  | Mahmoud Elsherbiny | Amina | Positive
TC_P_0010 | verify sorting functionality | User is on Homepage | Select sorting option (price : low to high) | Sorting option | Products rearange accordingly | N/A | Products appear sorted as selected | Functional | PASS | Typing functionality working as expected |  | Mahmoud Elsherbiny | Amina | Positive
TC_P_0011 | Test category filter | User is on Homepage | Select product category | Category name | Only products with in the selected category are shown | N/A | Category filter applied successfully | Functional | PASS | Information copied successfully |  | Mahmoud Elsherbiny | Amina | Positive
TC_P_0012 | Validate New Arrivals section | User is on Homepage | Click on New Arrivals tab | None | Latest products are listed correctly | N/A | User can see newly added product | UI | PASS | Content description displayed correctly |  | Mahmoud Elsherbiny | Amina | Positive
TC_P_0013 | Validate mobile responsiveness | User accesses site on mobile | Open homepage on a mobile browser | Mobile browser | page elements adjast correctly to screen size | N/A | UI adapts correctly to screen size | Functional | PASS | Location created successfully |  | Mahmoud Elsherbiny | Amina | Positive
TC_P_0014 | Check hover effects on products | User is on Homepage | Hover over product card | None | Products details display on hover | N/A | Hover effects work properly | Validation | PASS | Vendor product displayed correctly |  | Mahmoud Elsherbiny | Amina | Positive
TC_P_0015 | Test broken links | User is on Homepage | click all primary navigation links | Navigatoin links | All links function correctly | N/A | All primary links work without errors | UI | PASS | All links and content displayed properly |  | Mahmoud Elsherbiny | Amina | Positive
Bug Report
Defect-id | title | Description | Pre-condition | steps | postcondition | ER | AR | Severity | Priority | type | status | Version | Attachment
B_C_001 | Search with Location | The Location feature fails to return results when custom filters are applied |  | 1. Add items to cart 2. Proceed to checkout 3. Observe location auto-detection 4. Attempt manual location entry | System rolls back to registration step 2, preserves input data, and shows location error modal |  |  | High (Blocks registration) | P1 (Critical)
B_C_002
B_C_003
B_C_004
B_C_005
B_C_006
B_C_007
B_C_008

## Cart
Project Name | Furniture Market Place
module name | Cart
created by | Moaaz Besher
creation date | 2\5\2025
reviwed by | Mahmoud M.Abo Shark
reviwed date | 2025-05-09
executid by | Moaaz Besher
executid date | 2025-05-13
TC_ID | Title | Pre-condition | Steps | Test Data | Expected Result | Attachments if any | postcondition | Type | Status | Actual Result | BUG_ID | Created by | Reviewed by | Comments | executed by
TC_P_0001 | Spanish Language Verification | On cart page | 1. Click ES button 2. Check login text | N/A | Shows "Iniciar sesión" | N/A | N/A | Functional | Fail | Shows "Log In" | B_C_001 | Moaaz Besher | Mahmoud M.Abo Shark | Translation missing
TC_P_0002 | French Language Verification | On cart page | 1. Click FR button 2. Check login text | N/A | Shows "S'identifier" | N/A | N/A | Functional | Pass | Correct display | N/A | Moaaz Besher | Mahmoud M.Abo Shark
TC_P_0003 | English Language Verification | On cart page | 1. Click EN button 2. Check login text | N/A | Shows "Log In" | N/A | N/A | Functional | Pass | Correct display | N/A | Moaaz Besher | Mahmoud M.Abo Shark
TC_P_0004 | Support Link Navigation | On cart page | 1. Click Support link | N/A | Navigates to /support | N/A | Returns to cart | Functional | Pass | Correct navigation | N/A | Moaaz Besher | Mahmoud M.Abo Shark
TC_P_0005 | Cart Icon Functionality | On cart page | 1. Click Cart icon | N/A | Refreshes cart page | N/A | N/A | Functional | Pass | Page refreshed | N/A | Moaaz Besher | Mahmoud M.Abo Shark
TC_P_0006 | Header Login Navigation | On cart page | 1. Click Login link | N/A | Navigates to /login | N/A | Returns to cart | Functional | Pass | Correct navigation | N/A | Moaaz Besher | Mahmoud M.Abo Shark
TC_P_0007 | Header Signup Navigation | On cart page | 1. Click Signup link | N/A | Navigates to /account/create | N/A | Returns to cart | Functional | Pass | Correct navigation | N/A | Moaaz Besher | Mahmoud M.Abo Shark
TC_P_0008 | Empty Cart Redirection | Empty cart | 1. Click "Start shopping" | N/A | Navigates to homepage | N/A | N/A | Functional | Pass | Correct redirection | N/A | Moaaz Besher | Mahmoud M.Abo Shark
TC_P_0009 | Footer Login Navigation | On cart page | 1. Click footer Login | N/A | Navigates to /login | N/A | Returns to cart | Functional | Pass | Correct navigation | N/A | Moaaz Besher | Mahmoud M.Abo Shark
TC_P_0010 | Footer Signup Navigation | On cart page | 1. Click footer Signup | N/A | Navigates to /account/create | N/A | Returns to cart | Functional | Pass | Correct navigation | N/A | Moaaz Besher | Mahmoud M.Abo Shark
TC_P_0011 | Footer Search Navigation | On cart page | 1. Click footer Search | N/A | Navigates to /search | N/A | Returns to cart | Functional | Pass | Correct navigation | N/A | Moaaz Besher | Mahmoud M.Abo Shark
TC_P_0012 | Footer Popular Navigation | On cart page | 1. Click footer Popular | N/A | Navigates to /product/popular | N/A | Returns to cart | Functional | Pass | Correct navigation | N/A | Moaaz Besher | Mahmoud M.Abo Shark
TC_P_0013 | Footer Latest Navigation | On cart page | 1. Click footer Latest | N/A | Navigates to /product/latest | N/A | Returns to cart | Functional | Pass | Correct navigation | N/A | Moaaz Besher | Mahmoud M.Abo Shark
TC_P_0014 | Footer Sellers Navigation | On cart page | 1. Click footer Sellers | N/A | Navigates to /sellers | N/A | Returns to cart | Functional | Pass | Correct navigation | N/A | Moaaz Besher | Mahmoud M.Abo Shark
TC_P_0015 | Account Dropdown Functionality | Logged in | 1. Click account name 2. Test all options | Valid credentials | Correct page navigation | N/A | Logs out | Functional | Pass | All options worked | N/A | Moaaz Besher | Mahmoud M.Abo Shark | Includes: My Account, Messages, Purchases, Logout
TC_P_0016 | Price Calculation | Items in cart | 1. Sum individual prices 2. Compare with total | N/A | Total matches sum of items | N/A | N/A | Functional | Fail | Incorrect calculation | B_C_002 | Moaaz Besher | Mahmoud M.Abo Shark
TC_P_0017 | Remove item | Items in cart | 1. Note initial total price 2. Remove target item (ID: 242) 3. Confirm deletion 4. Verify: - Item removed from list - New total = Initial - item price | Item to remove: Rocking Chair (ID: 242) Initial Price: X ItemPrice:Y | 1. Item removed from cart 2. New total = $(X-Y) | N/A | N/A | Functional | Pass | 1. Item successfully removed 2. Price updated to $(X-Y) | N/A | Moaaz Besher | Mahmoud M.Abo Shark
TC_P_0018 | Update Quantity | Items in cart | 1. Edit quantity 2. Click Update | Product 301 New Qty: 5 | Quantity and price update | N/A | N/A | Functional | Pass | Updated successfully | N/A | Moaaz Besher | Mahmoud M.Abo Shark
TC_P_0019 | Checkout Flow | Items in cart | 1. Click Checkout 2. Verify redirection | N/A | Redirects to checkout page | N/A | Returns to cart | Functional | Pass | Redirected correctly | N/A | Moaaz Besher | Mahmoud M.Abo Shark
TC_P_0020 | Empty Cart Function | Items in cart | 1. Click "Empty Cart" 2. Confirm | N/A | Removes all items | N/A | N/A | Functional | Pass | Cart emptied successfully | N/A | Moaaz Besher | Mahmoud M.Abo Shark
Bug Report
Defect-id | title | Description | Pre-condition | steps | postcondition | ER | AR | Severity | Priority | type | status | Version | Attachment
B_C_001 | Spanish Translation Missing | ES language button shows English text | On cart page | 1. Click ES button 2. Observe text | N\A | "Iniciar sesión" | "Log In" | Medium | P2 | Functional | Open | Demo | N\A
B_C_002 | Price Calculation | Total price in cart page is not correct | Items in cart | 1. Sum individual prices 2. Compare with total | N\A | Total matches sum of items | Incorrect calculation | High | P1 | Functional | Open | Demo | N\A

## Checkout
Project Name | Furniture Market Place
module name | Checkout Page
created by | Amina
TC_ID | Pre-condition | TestScenario |  | TestCase |  | Steps |  |  |  | Expected Result |  | Actual Result | Status | BUG_ID | Priority
TS_01 | User is on Shopping cart page | Verify that the checkout page loads correctly |  | Loading Payment Card Pag with some products |  | 1- Click on "checkoutt" button |  |  |  | Navegation to the checkout page |  | Navegation to the checkout page | Pass |  | High
|  |  |  | Loading Payment Card Pag without any product |  | 1- Click on "checkoutt" button |  |  |  | The button is not exist |  | The button is not exist | Pass |  | High
TS_02 | User is on Checkout page | Verify that the user can enter his address correctly |  | invalid inputs (special characters , numbers , ....) |  | 1-Click on the label |  | 0-0-0-0-0-0-0 |  | User cannt enter invalid inputs |  | User cannt enter invalid inputs | Pass |  | High
2-Enter invaild inputs
|  |  |  | valid inputs |  | 1-Click on name label |  | Elmansoura |  | User can enter valid inputs |  | User can enter valid inputs | Pass |  | High
2-Enter valid input
|  |  |  | thare is a field or more are left empty . |  | 1-Click on the label |  |  |  | User cannt leave any field empty . |  | User cannt leave any field empty . | Pass |  | High
2- leave it empty
TS_03 | User is on Checkout page | Verify that the user can enter the zip code correctly |  | invalid inputs (special characters , letters , ....) |  | 1-Click on the label |  | qw- e |  | User cannt enter invalid inputs |  | User can enter invalid inputs | Fail | BR_002 | High
2-Enter invaild inputs
|  |  |  | valid inputs |  | 1-Click on name label |  | 1240805 |  | User can enter valid inputs |  | User can enter valid inputs | Pass |  | High
2-Enter valid input
|  |  |  | thare is a field or more are left empty . |  | 1-Click on the label |  |  |  | User cannt leave any field empty . |  | User cannt leave any field empty . | Pass |  | High
2- leave it empty
TS_04 | User is on Checkout page | Verify that the user can enter the nema on card correctly |  | invalid inputs (special characters , numbers , ....) |  | 1-Click on the label |  | 0-0-0- |  | User cannt enter invalid inputs |  | User cannt enter invalid inputs | Pass |  | High
2-Enter invaild inputs
|  |  |  | valid inputs |  | 1-Click on name label |  | alaa |  | User can enter valid inputs |  | User can enter valid inputs | Pass |  | High
2-Enter valid input
|  |  |  | thare is a field or more are left empty . |  | 1-Click on the label |  |  |  | User cannt leave any field empty . |  | User cannt leave any field empty . | Pass |  | High
2- leave it empty
TS_05 | User is on Checkout page | Verify that the user can enter the card number correctly |  | invalid inputs (special characters , letters , ....) |  | 1-Click on the label |  | qwe |  | User cannt enter invalid inputs |  | User cannt enter invalid inputs | Pass |  | High
2-Enter invaild inputs
|  |  |  | valid inputs |  | 1-Click on name label |  | 1234 1234 1234 1234 |  | User can enter valid inputs |  | User can enter valid inputs | Pass |  | High
2-Enter valid input
|  |  |  | thare is a field or more are left empty . |  | 1-Click on the label |  |  |  | User cannt leave any field empty . |  | User cannt leave any field empty . | Pass |  | High
2- leave it empty
TS_06 | User is on Checkout page | Verify that the user can enter the cvc correctly |  | invalid inputs (special characters , letters , ....) |  | 1-Click on the label |  | qwe |  | User cannt enter invalid inputs |  | User cannt enter invalid inputs | Pass |  | High
2-Enter invaild inputs
|  |  |  | valid inputs |  | 1-Click on name label |  | 123 |  | User can enter valid inputs |  | User can enter valid inputs | Pass |  | High
2-Enter valid input
|  |  |  | thare is a field or more are left empty . |  | 1-Click on the label |  |  |  | User cannt leave any field empty . |  | User cannt leave any field empty . | Pass |  | High
2- leave it empty
TS_07 | User is on Checkout page | Verify that the user can enter the cardExpiry correctly |  | invalid inputs (special characters , letters , more than4 num....) |  | 1-Click on the label |  | 1234567 |  | User cannt enter invalid inputs |  | User cannt enter invalid inputs | Pass |  | High
2-Enter invaild inputs
|  |  |  | valid inputs |  | 1-Click on name label |  | 09 09 |  | User can enter valid inputs |  | User can enter valid inputs | Pass |  | High
2-Enter valid input
|  |  |  | thare is a field or more are left empty . |  | 1-Click on the label |  |  |  | User cannt leave any field empty . |  | User cannt leave any field empty . | Pass |  | High
2- leave it empty
TS_08 | User is on Checkout page | Verify that the user can enter the email correctly |  | invalid inputs |  | 1-Click on the label |  | a |  | User cannt enter invalid inputs |  | User cannt enter invalid inputs | Pass |  | High
2-Enter invaild inputs
|  |  |  | valid inputs |  | 1-Click on name label |  | john.doe@example.com |  | User can enter valid inputs |  | User can enter valid inputs | Pass |  | High
2-Enter valid input
|  |  |  | thare is a field or more are left empty . |  | 1-Click on the label |  |  |  | User cannt leave any field empty . |  | User cannt leave any field empty . | Pass |  | High
2- leave it empty
TS_09 | User is on Checkout page | Verify that the email matches the confirmation email |  | inputs does not match |  | 1-Enter an email |  | john.doe@ele.com , j.d@example.com |  | User cannt enter invalid inputs |  | User can enter invalid inputs | Fail | BR_001 | High
2-Enter another one
|  |  |  | Mismatched inputs |  | 1-Click on name label |  | john.doe@example.com |  | User can enter valid inputs |  | User can enter valid inputs | Pass |  | High
2-Enter valid input
|  |  |  | thare is a field or more are left empty . |  | 1-Click on the label |  |  |  | User cannt leave any field empty . |  | User cannt leave any field empty . | Pass |  | High
2- leave it empty
Bug Report
Defect-id | title | Description | Pre-condition | steps | postcondition | ER | AR | Severity | Priority | type | status | asign to
BR_001 | Confimation of email | Issue with Email Confirmation | User is on Checkout page |  |  | User cannt enter invalid inputs | User can enter invalid inputs | High | High | Functional | Open | Backend developer
1-Enter an email
Email is not registered correctly
2- Enter another one
BR_002 | invalid inputs of zip code | Issue with zip code | User is on Checkout page |  |  | User cannt enter invalid inputs | User can enter invalid inputs | High | High | Functional | Open | Backend developer
|  |  |  | Enter invalid zip code | zip code is not registered correctly

## UI & Responsive
Project Name | Furniture Market Place
module name | UI & Responsive
created by | Alaa
TC_ID | TestScenario |  | Pre-condition | Steps |  | Expected Result |  |  |  | Actual Result |  |  | Status | BUG_ID | Priority
TC-UI-01 | Verify page title and branding |  | User is on the home page | 1. Open the website. |  | Title and logo are displayed correctly and match the brand identity. |  |  |  | Title and logo are displayed correctly and match the brand identity. |  |  | Pass |  | High
2. Check the page title and logo.
TC-UI-02 | Verify font consistency |  | User is on the home page | 1. Navigate across pages |  | Fonts are consistent across all pages |  |  |  | Fonts are consistent across all pages |  |  | Pass |  | High
2. Check font styles (size, family, weight).
TC-UI-03 | Verify button styles |  | User is on the home page | 1. Check all buttons (hover, active, disabled states). |  | Buttons are visually consistent and interactive. |  |  |  | Buttons are visually consistent and interactive. |  |  | Pass |  | High
2. Verify size and alignment.
TC-UI-04 | Verify icon visibility |  | User is on the home page | 1. Check all icons |  | Icons are clear and correctly placed. |  |  |  | Icons are clear and correctly placed. |  |  | Pass |  | High
2. Ensure they are properly aligned.
TC-UI-05 | Verify photo of home page visibility |  | User is on the home page | 1. Open the website. |  | Photo of home page is displayed correctly and match the figma design. |  |  |  | Photo of home page is displayed correctly and match the figma design. |  |  | Pass |  | High
2- Check the photo of home page
TC-UI-06 | Verify search-criteria-bar visibility |  | User is on the home page | 1. Open the website. |  | search-criteria-bar is displayed correctly and match the figma design. |  |  |  | search-criteria-bar is displayed correctly and match the figma design. |  |  | Pass |  | High
2- Check the search-criteria-bar
TC-UI-07 | Verify Popular items visibility |  | User is on the home page | 1. Open the website. |  | popular items are displayed correctly and match the figma design. |  |  |  | popular items are displayed correctly and match the figma design. |  |  | Pass |  | High
2- Scroll down to the popular items
TC-UI-08 | Verify promotions-block visibility |  | User is on the home page | 1. Open the website. |  | promotions-block is displayed correctly and match the figma design. |  |  |  | promotions-block is displayed correctly and match the figma design. |  |  | Pass |  | High
2- Scroll down to the promotions-block
TC-UI-09 | Verify seller-list visibility |  | User is on the home page | 1. Open the website. |  | seller-list is displayed correctly and match the figma design. |  |  |  | seller-list is displayed correctly and match the figma design. |  |  | Pass |  | High
2- Scroll down to the seller-list
TC-UI-10 | Verify the background of seller-list visibility |  | User is on the home page | 1. Open the website. |  | back ground photo of seller-list is displayed correctly and match the figma design. |  |  |  | back ground photo of seller-list is displayed correctly and match the figma design. |  |  | Pass |  | High
2- Scroll down to the seller-list
TC-UI-11 | Verify the cart-item visibility |  | User is on the cart page | 1. Navegate to cart page. |  | back ground photo of seller-list is displayed correctly and match the figma design. |  |  |  | back ground photo of seller-list is displayed correctly and match the figma design. |  |  | Pass |  | High
2- Check the items in cart
TC-UI-12 | Verify the seller data of the cart-item visibility |  | User is on the cart page | 1. Navegate to cart page. |  | the photo and the name are displayed correctly and match the figma design. |  |  |  | the photo and the name of seller arent displayed correctly and match the figma design. |  |  | Fail | BR_001 | Medium
2- Check the seller data of items in cart
TC-UI-13 | Verify the summary in the cart-item visibility |  | User is on the cart page | 1. Navegate to cart page. |  | the summary is displayed correctly and match the figma design. |  |  |  | the summary is displayed correctly and match the figma design. |  |  | Pass |  | High
2- Check the summary
TC-UI-14 | Verify the checkout button in the cart-item visibility |  | User is on the cart page | 1. Navegate to cart page. |  | the checkout button is displayed correctly and match the figma design. |  |  |  | the checkout button is displayed correctly and match the figma design. |  |  | Pass |  | High
2- Check the checkout button
TC-UI-15 | Verify the empty button in the cart-item visibility |  | User is on the cart page | 1. Navegate to cart page. |  | the empty button is displayed correctly and match the figma design. |  |  |  | the empty button is displayed correctly and match the figma design. |  |  | Pass |  | High
2- Check the empty button
TC-UI-16 | Verify the Technical Questions cart in the Support page visibility |  | User is on the Support page | 1. Navegate to Support page. |  | the Technical Questions cart is displayed correctly and match the figma design. |  |  |  | the Technical Questions cart is displayed correctly and match the figma design. |  |  | Pass |  | High
2- Check Technical Questions cart
TC-UI-17 | Verify the Order Questions cart in the Support page visibility |  | User is on the Support page | 1. Navegate to Support page. |  | Order Questions cart is displayed correctly and match the figma design. |  |  |  | Order Questions cart is displayed correctly and match the figma design. |  |  | Pass |  | High
2- Check Order Questions cart
TC-UI-18 | Verify the Loin form in the login page visibility |  | User is on the login page | 1. Navegate to Support page. |  | login form is displayed correctly and match the figma design. |  |  |  | login form cart is displayed correctly and match the figma design. |  |  | Pass |  | High
2- Check login form
TC-UI-19 | Verify the sign up form in the login page visibility |  | User is on the sign up page | 1. Navegate to Support page. |  | sign up form is displayed correctly and match the figma design. |  |  |  | sign up form cart is displayed correctly and match the figma design. |  |  | Pass |  | High
2- Check sign up form
Bug Report
Defect-id | title | Description | Pre-condition | steps | postcondition | ER | AR | Severity | Priority | type | status | asign to
BR_001 | Seller INFO | the photo and the name of seller arent displayed correctly and match the figma design. | User is on the cart page | 1. Navegate to cart page. |  | the photo and the name are displayed correctly and match the figma design. | the photo and the name of seller arent displayed correctly and match the figma design. | High | Meduim | UI & Functional | Open | FrontEnd Developer
2- Check the seller data of items in cart

## ProductPage
Project Name |  | Furniture Market Place
module name |  | ProductPage
created by |  | Alaa
TS_ID | Test Scenario |  | Precondition |  | Steps |  | Expected Result |  |  | Actual Result |  | Status | BUG_ID | Priority
TSD_01 | Verify Product Title |  | user is on product page |  | Open the Rocking Chair product page |  | Product title should be "Rocking Chair" |  |  | Product title is "Rocking Chair" |  | Pass |  | High
TSD_02 | Verify Product Images Display |  |  |  | Click on both product images |  | Both images should load correctly |  |  | Both images are loaded correctly |  | Pass |  | High
TSD_03 | Add Product to Cart |  |  |  | Click "Add to Cart" |  | Product should be added to cart with confirmation |  |  | Product is added to cart with confirmation |  | Pass |  | High
TSD_04 | Verify thet user can add valid Quantity |  |  |  | Enter any too much num |  | allows a specific quantity based on the available stock |  |  | any number is accepted |  | Fail | BR_oo1 | Medium
TSD_05 | Validate Quantity Input |  |  |  | Enter invalid quantity (e.g., negative number) |  | Error message should display indicating valid input |  |  | Error message appears |  | Pass |  | High
TSD_06 | Contact Seller Button |  |  |  | Click on "Contact Seller" button |  | User should be able to contact with the seller |  |  | User are able to contact with the seller |  | Pass |  | Medium
TSD_07 | Navigate to Seller Profile |  |  |  | Click on seller name link |  | Redirected to seller profile page |  |  | Redirected to seller profile page |  | Pass |  | Medium
TSD_08 | Eadcrumb Navigation |  |  |  | Click on breadcrumb links |  | Should navigate through each category link successfully |  |  | navigate through each category link successfully |  | Pass |  | Medium
TSD_09 | Rating display |  |  |  | Check product rating section |  | Default unselected stars should be shown |  |  | Default unselected stars should be shown |  | Pass |  | Medium
TSD_10 | Rating functonalty |  |  |  | try to rate |  | User should be able to rate |  |  | user cannt rate |  | Fail | BR_002 | Medium
Bug Report
Bug_ID | title | Description |  | Pre-condition |  | steps |  | postcondition | ER |  | AR |  |  |  | Priority | Severity | type | status | asign to
BR_001 | Adding Valid Quantity | Issue with Adding Valid Quantity on Product Page |  | user is on product page |  | Enter any too much num |  |  | allows a specific quantity based on the available stock |  | any number is accepted |  |  |  | Medium | High | Functional | Open | Backend developer
BR_002 | Rating functonalty | Issue with Rating Functionality |  | user is on product page |  | Try to rate |  |  | User should be able to rate |  | user cannt rate |  |  |  | Medium | High | Functional | Open | Backend developer